## Gantt Chart
| Year 2020 |  | Month | January |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  |  | July |  |  |  | August |  |  |  |  | September
|  | Dur-n (wks) | Date | 2020-01-06 | 2020-01-13 | 2020-01-20 | 2020-01-27 | 2020-02-03 | 2020-02-10 | 2020-02-17 | 2020-02-24 | 2020-03-02 | 2020-03-09 | 2020-03-16 | 2020-03-23 | 2020-03-30 | 2020-04-06 | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11 | 2020-05-18 | 2020-05-25 | 2020-06-01 | 2020-06-08 | 2020-06-15 | 2020-06-22 | 2020-06-29 | 2020-07-06 | 2020-07-13 | 2020-07-20 | 2020-07-27 | 2020-08-03 | 2020-08-10 | 2020-08-17 | 2020-08-24 | 2020-08-31 | 2020-09-07 | 2020-09-14 | 2020-09-21 | 2020-09-28
Ind | Activity |  | week n | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39
A | Prepare land for construction works | 3
B | Excavate foundations (Digging) | 2
C | Build foundation structure | 4
D | Build Showroom spaces (floor 1) | 9
E | Complete Roof works | 6
G | Install doors and windows | 3
I | Finalize external building façade | 2
H | Connect/install Utilities systems | 3
J | Interior works | 7
F | Design interiors | 2
O | Car Selection for the exhibition | 2
P | Car manufacturing | 24
Q | Position cars in the showroom area | 1
K | Visual Effect systems - Creation | 6
L | Visual Effect systems - Montage | 4
M | Recruit Personnel | 8
N | Train Personnel | 2
X | Grand Opening Preparation | 3
Z | Grand Opening | 0 | [33 empty] | FINISH
Gantt Chart