## Actions Log
No. | Action | Owner | Due Date | Comments
1 | Update Project Schedule to reflect new duration of the "recruit personnel" activity. Increase to 11 weeks. If PM pushes the Due Date by 3 weeks, this will be the new Critical path. Hence, PM to change the start date, in order to keep the initial buffer: -Change start date to 13-Apr, instead of 4-May. Update project plans | Project Manager | 2020-02-04
…
3
5
6
7
8
9
10
11
12
13 | Negotiate and sign an agreement with a new Design agency in the next 2 weeks. Marketing manager to participate the negotiation, in order to ensure the requirements are understood by the new vendor and added to the contract. | Finance manager Assistant | 2020-06-03
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
Project Diary