## Project schedule
N | Activity | Start Date | End Date | Status
1 | Requirements definition | 2026-03-02 | 2026-04-10 | Ongoing
1.1 | Requirements gathering | 2026-03-02 | 2026-03-20 | Delayed
1.2 | Technical specs confirmed | 2026-03-23 | 2026-03-27 | Not Started
1.3 | Vendor negotiations | 2026-03-09 | 2026-04-10 | Ongoing
2 | Project Kick Off | 2026-04-13 | 2026-04-13 | Not Started
3 | System development | 2026-04-20 | 2026-07-31 | Not Started
3.1 | Coding Part A | 2026-04-20 | 2026-05-15 | Not Started
3.2 | Coding Part B | 2026-05-18 | 2026-06-26 | Not Started
3.3 | Coding Part C | 2026-06-29 | 2026-07-31 | Not Started
4 | Integration Testing | 2026-08-03 | 2026-08-28 | Not Started
5 | User Acceptance Testing | 2026-08-03 | 2026-10-02 | Not Started
6 | Rollout to business units | 2026-10-05 | 2026-11-16 | Not Started
6.1 | User Training | 2026-10-05 | 2026-11-06 | Not Started
6.2 | Smoke testing | 2026-10-19 | 2026-11-13 | Not Started
6.3 | Cutover & Go Live | 2026-11-16 | 2026-11-16 | Not Started
7 | Support period | 2026-11-16 | 2027-01-29 | Not Started
8 | Project closure | 2027-02-01 | 2027-02-05 | Not Started