## Decision Matrix
DECISION MATRIX FOR [ABC]
Options
Criteria | Weight | A | B | C | D | E | Max
Criteria 1 | 50% | 93 | 95 | 60 | 82 | 65 | 95
Criteria 2 | 20% | 75 | 85 | 75 | 77 | 74 | 85
Criteria 3 | 15% | 85 | 92 | 80 | 87 | 64 | 92
Criteria 4 | 10% | 85 | 81 | 72 | 83 | 65 | 85
Criteria 5 | 5% | 90 | 88 | 77 | 81 | 73 | 90
Score | 100% | 87.25 | 90.8 | 68.05 | 81.8 | 67.05 | 90.8
Price |  | 260000 | 250000 | 210000 | 230000 | 190000 | 260000
Value |  | 0.9609 | 1.04 | 0.92789 | 1.0184 | 1.0105 | 1.04
Use
* This document provides an objective way to choose between several options, by comparing their scores across several weighted criteria. If you are choosing between several costed options, it also then provides a best value scoring by comparing the scores against the option prices.
Adding Criteria
* Add criteria rows if needed, ideally inserted between the existing Criteria 1 and Criteria 5 so the formatting will not need to be updated.
* If criteria rows are added, update the Score column formulas to include the new criteria. You should be able to update one formula, and just copy it to the other options.
* If criteria rows are added, update the corresponding Max column by copying over an existing Max cell.
Deleting Criteria
* Delete criteria rows if needed, ideally Criteria 2, 3, or 4 so the formatting will not need to be updated. It may be easier to just leave unused criteria rows, and set the weight to 0%.
* If criteria rows are deleted, delete the corresponding elements of the Score formula. You should be able to update one formula, and just copy it to the opther options.
Adding Options
* Add options if needed, ideally inserting between Options A and E so the formatting, and formulas in the Max column, do not need to be updated.
* If options are added, copy over the Score and Value formulas from an existing option.
Deleting Options
* Delete options if needed, ideally Options B, C, or D so the Max column formulas are not affected.
For more information, refer to the Deeply Practical Project Management (DPPM) reference book Amazon.com/dp/1548650463/ or online course at DeeplyPracticalPM.com In particular see the chapter "Planning". © 2020-10-10 William Stewart DeeplyPracticalPM.com