## Estimating
Estimate For Deliverable: | Process Update Draft 1
Owner: | A. Allen
Duration (days): | 80.8913
Material & services cost: | 2680
Resources cost: | 52917.6471
Total cost | 55597.6471
Resource: | Process Lead (Sr.) | Business Analyst (Int.) | System Analyst (Int.) | User Rep. | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | Totals (Hours) | Max Duration (Days)
Hours a day: | 8 | 8 | 8 | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Productivity: | 85% | 85% | 85% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Availability: | 100% | 50% | 33% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | Material & Services
Rate / hour: | 100 | 80 | 80 | 60 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | Item | Qty | Cost | Subtotal
Kick-off | 4 | 4 | 4 | 4 | [8 empty] | 16 | 1.7825 | Food | 4 | 20 | 80
Requirements review | 4 | 4 | 4 | 4 | [8 empty] | 16 | 1.7825 |  |  |  | 0
Best practices review | 4 | 2 | 2 | [9 empty] | 8 | 0.89127 |  |  |  | 0
Readiness review | 4 | 2 | 2 | [9 empty] | 8 | 0.89127 |  |  |  | 0
Review existing processes | 16 | 16 | 16 | 8 | [8 empty] | 56 | 7.1301 |  |  |  | 0
Identify update processes | 8 | 8 | 4 | 4 | [8 empty] | 24 | 2.3529 |  |  |  | 0
Analyze efficiency updates | 16 | 16 | 8 | 4 | [8 empty] | 44 | 4.7059 |  |  |  | 0
Flowchart processes | 4 | 8 | 16 | [9 empty] | 28 | 7.1301 | Software update | 1 | 400 | 400
Identify unnecessary steps | 12 | 12 | 4 | 2 | [8 empty] | 30 | 3.5294 |  |  |  | 0
Identify duplicate steps | 12 | 12 | 4 | 1 | [8 empty] | 29 | 3.5294 |  |  |  | 0
Identify parallel steps | 24 | 24 | 8 | 2 | [8 empty] | 58 | 7.0588 |  |  |  | 0
Identify automation steps | 8 | 16 | 16 | 2 | [8 empty] | 42 | 7.1301 |  |  |  | 0
Document new processes | 8 | 16 | 24 | 2 | [8 empty] | 50 | 10.6952 | Full size colour printing | 1 | 850 | 850
Peer review | 4 | 8 | 8 | [9 empty] | 20 | 3.5651 | Video conference rental | 2 | 250 | 500
Update processes | 4 | 8 | 8 | 1 | [8 empty] | 21 | 3.5651 |  |  |  | 0
User review | 4 | 4 | 4 | 4 | [8 empty] | 16 | 1.7825 |  |  |  | 0
Update processes | 8 | 12 | 16 | [9 empty] | 36 | 7.1301 |  |  |  | 0
User approval | 2 | 2 | 2 | 2 | [8 empty] | 8 | 0.89127 |  |  |  | 0
Final document | 4 | 8 | 12 | 1 | [8 empty] | 25 | 5.3476 | Full size colour printing | 1 | 850 | 850
Effort hours | 150 | 182 | 162 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 535 | 80.8913 | Risk Drivers |  |  | 2680
Effort days | 18.75 | 22.75 | 20.25 | 5.125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66.875 | Could increase effort: | 1. Unavailability of matrixed team, or user representative, due to other requirements. 2. Unusually complex interfaces with external elements.
Productive hours | 176.4706 | 214.1176 | 190.5882 | 48.2353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 629.4118
Productive days | 22.0588 | 26.7647 | 23.8235 | 6.0294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78.6765
Duration hours | 176.4706 | 428.2353 | 577.5401 | 96.4706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1278.7166 | Could decrease effort: | 1. High-level authorization of User Rep to call on people and resources to obtain timely information when required. 2. Project management course for entire team :-)
Duration days | 22.0588 | 53.5294 | 72.1925 | 12.0588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159.8396
Costs | 17647.0588 | 17129.4118 | 15247.0588 | 2894.1176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52917.6471
Use
CODING: White cells are for entry, grey are for results (do not change). Enter times in hours not days.
ACTIVITIES: If work by several Resources happens at the same time, enter on the same Activity, otherwise enter on separate Activities so the Max Duration column and overall Duration add them up.
MATERIAL & SERVICES: If there are multiple items for one Activity, enter on separate Activities rows, perhaps named for the material or service item, but without any Resource times.
PRODUCTIVITY: Includes benefits, usually maximum 85% even for full-time. For large projects if it includes the vacation percentage across the year, make sure the finance department is aware how much so they can back it out for costing, or add a row below the Productivity percentage for Vacation percentage and separate Productive hours for scheduling and Costed hours without the vacation percentage to make it easy for them.
DURATION: The spreadsheet includes this calculation, as a sum of the column Max Duration, which takes into account each resource’s time estimate, length of day, and availability. If you add more columns for more resources, this formula in the Max Duration column must be extended. Note that this can instead be included in most Gantt schedule tools instead, where the Gantt application will apply the length of day and availability to produce actual calendar duration, so if you choose to use the Gantt schedule functionality for this instead, then do not use the functionality in this spreadsheet, removing the rows Hours a day, Productivity, Duration hours, and Duration days, and the column Max Duration.
Changes
ACTIVITIES: If you insert rows for activities, make sure you copy the formulas from an existing row into their Max Duration and Material & Service Subtotal columns (in this template, columns P and T).
RESOURCES (LESS): You can hide columns if not needed, however make sure the Activities have no entries, and set the Hours, Productivity, Availability, and Rate/Hour all to the number 1 (in this template, rows 10 to 13).
RESOURCES (MORE): If you need to add more than the default twelve Resources, make sure you update the formulas in the Max Duration column to include them (in this template, column P).
For more information, refer to the Deeply Practical Project Management (DPPM) reference book Amazon.com/dp/1548650463/ or online course at DeeplyPracticalPM.com In particular see the chapter "Planning". © 2020-10-10 William Stewart DeeplyPracticalPM.com
.