## Monthly Report
G | Scope & Schedule |  | R |  |  |  | Cost |  |  |  | Y
|  |  |  | Milestone |  |  |  |  | CPI | SPI
|  |  |  | Milestone 1 |  |  |  |  | 0.92 | 0.81
|  |  |  | Milestone 2 |  |  |  |  | 0.94 | 0.84
|  |  |  | Milestone 3 |  |  |  |  | 0.86 | 0.86
:
:
:
(Any cost data avail; this example uses earned value info.)
|  |  |  | Total |  |  |  |  | 0.94 | 0.88
|  |  |  | BAC = | 7.4M | EAC = | $7.8M | ETC = | $3.2M | VAC = | $0.4M
|  | Issues |  |  |  |  | Customer
* Major issues, top three maximum, their status, and any assistance required. * ... * ... |  |  |  | * The end-user of the project, whatever is relevant, anything on their mind, the status of user reviews, any satisfaction metrics, any assistance required. * ... * ... * ... * ...
Risks
* Major risks, top three maximum, their status, and any assistance required. * Risk register can be on hand as backup if requested. * ...
For more information, refer to the Deeply Practical Project Management (DPPM) reference book Amazon.com/dp/1548650463/ or online course at DeeplyPracticalPM.com In particular see the chapter "Monitoring & Control". © 2020-10-10 William Stewart DeeplyPracticalPM.com
.