## Risk Register
Risk Register For Project: | Great Things |  |  |  | 0 |  |  |  |  | 0
Project Manager: | A. Allen |  |  |  | 0 |  |  |  |  | 0
Version Date: | YYYY-MM-DD | [8 empty] | 0
|  | Before Response Planning |  |  |  |  | After Response Planning
Risk | Risk Statement | P% | T (d) | $K | P x T | P x $ | P% | T (d) | $K | P x T | P x $ | Owner | Trigger | Response Plan | Backup Plan | Resolution Date
Team Turnover | If we lose people on the team, we will have to replace them, causing schedule and cost delays. | 30% | 25 | 50 | 7.5 | 15 | 20% | 20 | 40 | 4 | 8 | B. Baker | Staff complains about environment and pay. | Cross train personnel, pay staff appropriately, provide managers with management training, focus on team morale, hold bi-monthly social events. | Identify backup staff from within the organization, and be ready to quickly bring on consultant expertise if possible. | 20XX-MM-DD
Personnel Unavailability |  |  |  |  | 0 | 0 |  |  |  | 0 | 0
Approval Delays |  |  |  |  | 0 | 0 |  |  |  | 0 | 0
Software Development Issues |  |  |  |  | 0 | 0 |  |  |  | 0 | 0
Interface Issues |  |  |  |  | 0 | 0 |  |  |  | 0 | 0
Contractor Issues |  |  |  |  | 0 | 0 |  |  |  | 0 | 0
Scope Changes |  |  |  |  | 0 | 0 |  |  |  | 0 | 0
Problems At End
[5 empty] | 0 | 0 |  |  |  | 0 | 0
Total Risk Budget: |  |  |  |  | 7.5 | 15 |  |  |  | 4 | 8
Use
CODING: White cells are for user entry, gray cells are for results.
RISKS (MORE): If you insert rows for more risks, make sure you copy the formulas from an existing row into the PxT and PX$ columns.
RISKS (LESS): You can delete rows if not needed.
BEFORE & AFTER RESPONSE PLANNING: This register shows the risk calculations for both before and after response planning, so management can see how much the risks improved during project planning. As the project progresses, it is common to hide the columns for before planning, or make a copy of this sheet and then delete those columns in the working copy used as execution proceeds.
SECONDARY RISKS: For larger projects you sometimes also include secondary risks, the risks to the response plan solutions.
SECOND LAST ROW: The second last row, above the last row Total Risk Budget, is blank, so the register can be sorted, for example by the After Risk Planning column Px$, without affecting the last row.
For more information, refer to the Deeply Practical Project Management (DPPM) reference book Amazon.com/dp/1548650463/ or online course at DeeplyPracticalPM.com In particular see the chapter "Planning". For a realistic example of this document see the Magical Devices Version 3 (MDV3) project available with the online course and at DeeplyPracticalPM.com. © 2021-08-11 William Stewart DeeplyPracticalPM.com
.