## Simple
N. | Expense/Cost name | Budget ($) | Actual ($)
| Project | 0 | 0
1 | Expense A
2 | Expense B
3 | Expense C
4
5
6
7
8
9
10
Budget (Simple)

## Units
N. | Material / Activity | Units (#) | $/Unit | Budget | Actual | Balance
| Project |  |  | 80420 | 0 | 80420
1 | Material Type 1 | 1000 | 12 | 12000
2 | Material Type 2 | 250 | 25 | 6250
3 | Material Type 3 | 4000 | 7 | 28000
4 | Service Type 1 | 3000 | 11 | 33000
5 | Material Type 4 | 15 | 78 | 1170
6
7
8
9
10
Budget (Units)

## Travels
[13 empty] | TOTAL | 5251 | 29400
N | Name | Travel Reason | From | To | Duration (Days) | Status | Travel to | Travel From | Flight $ | Additional Travel $ | Total Travel $ | Hotel $ | Allowances $ | Total Trip $ | BUDGET
1 | Employee A, Trip 1 | Vendor negotiations | 2018-05-01 | 2018-05-11 | 10 | Done | London | New York | 1211 | 240 | 1451 | 2800 | 1000 | 5251 | 6000
2 | Employee A, Trip 2 | Vendor negotiations | 2018-05-20 | 2018-05-26 | 6 | On-going | London | New York |  |  | 0 |  |  | 0 | 4000
3 | Employee B, Trip 1 | Recruitment | 2018-05-01 | 2018-05-11 | 10 | Done | London | Singapore |  |  | 0 |  |  | 0 | 6000
4 | Employee C, Trip 1 | Recruitment | 2018-05-01 | 2018-05-04 | 3 | Done | London | Paris |  |  | 0 |  |  | 0 | 1000
5 | Employee C, Trip 2 | Recruitment | 2018-05-14 | 2018-05-18 | 4 | Done | London | Paris |  |  | 0 |  |  | 0 | 1200
6 | Employee C, Trip 3 | Recruitment | 2018-05-28 | 2018-06-01 | 4 | Booked | London | Paris |  |  | 0 |  |  | 0 | 1200
| Total MAY | [12 empty] | 5251 | 19400
7 | Employee A, Trip 3 | Vendor negotiations | 2018-06-04 | 2018-06-08 | 4 | Booked | London | New York |  |  | 0 |  |  | 0 | 3000
8 | Employee B, Trip 2 | Recruitment | 2018-06-04 | 2018-06-15 | 11 | Planned | London | Singapore |  |  | 0 |  |  | 0 | 7000
9 | [13 empty] | 0
| Total JUNE | [12 empty] | 0 | 10000
Budget (Business Travel)

## Project or Program
| 2020 | [10 empty] | Total Budget (per activity)
Project Overall Budget | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov
Prepare land for construction works | 2020 Jan: 3000 | 3000
Excavate foundations (Digging activities) | 2020 Jan: 10000 | 10000
Build foundation structure | 2020 Feb: 250000; 2020 Mar: 250000 | 500000
Build Showroom spaces (floor 1) | 2020 Mar: 450000; 2020 Apr: 450000 | 900000
Complete Roof works | 2020 May: 125000; 2020 Jun: 125000 | 250000
Design interiors | 2020 Mar: 25000 | 25000
Install doors and windows | 2020 Jun: 75000; 2020 Jul: 50000 | 125000
Connect/install Utilities systems | 2020 May: 20000; 2020 Jun: 10000 | 30000
Finalize external building façade | 2020 Aug: 35000 | 35000
Interior works | 2020 Jun: 75000; 2020 Jul: 100000 | 175000
Visual Effect systems - Creation | 2020 May: 35000 | 35000
Visual Effect systems - Montage | 2020 Jun: 15000 | 15000
Recruit Personnel | 2020 May: 15000; 2020 Jun: 15000 | 30000
Train Personnel | 2020 Jun: 5000; 2020 Jul: 5000 | 10000
Car Selection for the exhibition | 2020 Jan: 2000 | 2000
Car manufacturing | 2020 Feb: 60000; 2020 Mar: 60000; 2020 Apr: 60000; 2020 May: 60000; 2020 Jun: 60000 | 300000
Position cars in the showroom area | 2020 Jul: 5000 | 5000
Grand Opening Preparation | 2020 Jul: 25000 | 25000
Grand Opening | 2020 Aug: 25000 | 25000
Total Budget (per Month) | 15000 | 310000 | 785000 | 510000 | 255000 | 380000 | 185000 | 60000 | 0 | 0 | 0 | 2500000
Budget (Overall Project/Program)