## Milestone Table
Activity / Milestone | Start Date | End Date | Status
Project Kick Off | 2020-01-06 | 2020-01-06 | Not started
Prepare land for construction works | 2020-01-06 | 2020-01-24 | Not started
Excavate foundations (Digging) | 2020-01-27 | 2020-02-07 | Not started
Build foundation structure | 2020-02-10 | 2020-03-06 | Not started
Build Showroom spaces (floor 1) | 2020-03-09 | 2020-05-08 | Not started
Complete Roof works | 2020-05-11 | 2020-06-19 | Not started
Main construction Completed | 2020-06-19 | 2020-06-19 | Not started
Install doors and windows | 2020-06-22 | 2020-07-10 | Not started
Finalize external building façade | 2020-07-13 | 2020-07-24 | Not started
Connect/install Utilities systems | 2020-05-11 | 2020-05-29 | Not started
Interior works | 2020-06-01 | 2020-07-17 | Not started
Design interiors | 2020-03-09 | 2020-03-20 | Not started
Car Selection for the exhibition | 2020-01-06 | 2020-01-17 | Not started
Car manufacturing | 2020-01-20 | 2020-07-03 | Not started
Car manufacturing Completed (6 vehicles) | 2020-07-03 | 2020-07-03 | Not started
Position cars in the showroom area | 2020-07-06 | 2020-07-10 | Not started
Visual Effect systems - Creation | 2020-03-23 | 2020-05-01 | Not started
Visual Effect systems - Montage | 2020-06-22 | 2020-07-17 | Not started
Recruit Personnel | 2020-05-04 | 2020-06-26 | Not started
Train Personnel | 2020-06-29 | 2020-07-10 | Not started
Presonnel preparation Completed | 2020-07-10 | 2020-07-10 | Not started
Grand Opening Preparation | 2020-07-27 | 2020-08-14 | Not started
Grand Opening | 2020-08-15 | 2020-08-15 | Not started
Milestone Table